## Sheet1
Risk ID | Risk Description | Likelihood | Impact | Risk Rating | Mitigation / Control Measures | Responsible Person | Status
1 | Data Quality Issues (missing or inconsistent entries in the crime dataset) | High | High | High | Perform data cleaning, handle missing values, validate data consistency, and document cleaning process. | Data Engineer / Team Lead | Ongoing
2 | Ethical Bias in AI Model (bias inherited from historical data) | Medium | High | High | Use fairness metrics, bias detection tools, and ethical AI frameworks to ensure responsible AI outcomes. | Ethics Officer / AI Engineer | Planned
3 | Scope Creep during client feedback sessions | Medium | Medium | Medium | Establish clear project scope in charter, get written approvals for any change requests. | Project Lead | Ongoing
4 | Team Coordination and Resource Risk (intern-level project) | High | Medium | High | Hold regular stand-up meetings, use Agile sprints, assign clear roles in GitHub project board. | Scrum Master | Ongoing
5 | Model Accuracy Below Target (below 80%) | High | High | High | Optimize algorithms, test multiple models, enhance feature engineering, document evaluation results. | AI Engineer | Planned
6 | Technical Failures / Environment Issues ( Google Colab errors, dependencies) | Medium | Medium | Medium | Maintain version control, backup environments, and test on multiple platforms (Colab, VS Code). | Technical Lead | Ongoing
7 | Time Management and Deadline Delays | Medium | High | High | Create a detailed project schedule with milestones, track progress weekly, use MS Project and GitHub. | Scrum Master / Project Lead | Ongoing
8 | Client Feedback Delays or Miscommunication | Medium | Medium | Medium | Schedule regular check-ins, confirm meeting notes via email, and update progress logs. | Project Lead | Ongoing
9 | Data Confidentiality / Misuse Risk | Low | High | Medium | Ensure dataset is open-source, anonymized, and compliant with GDPR and university ethical guidelines. | Ethics Officer | Completed
10 | Loss of Work / GitHub Repository Issues | Medium | High | High | Use GitHub version control, backup data weekly, maintain local copies of code and documentation. | All Team Members | Ongoing

## Risk Heatmap
Risk Assessment Heat Map (All 10 Risks)
Risk ID | Risk Description | Likelihood | Impact | Risk Rating
1 | Data Quality Issues | High | High | High
2 | Ethical Bias in AI Model | Medium | High | High
3 | Scope Creep during client feedback sessions | Medium | Medium | Medium
4 | Team Coordination and Resource Risk (intern-level project) | High | Medium | High
5 | Model Accuracy Below Target (below 80%) | High | High | High
6 | Technical Failures / Environment Issues | Medium | Medium | Medium
7 | Time Management and Deadline Delays | Medium | High | High
8 | Client Feedback Delays or Miscommunication | Medium | Medium | Medium
9 | Data Confidentiality / Misuse Risk | Low | High | Medium
10 | Loss of Work / GitHub Repository Issues | Medium | High | High