## Sheet1
WBS ID | Level / Phase | Task / Deliverable | Description
1.0 | Project Initiation |  | Establish project foundation and goals.
1.1 | Project Initiation | Project Charter | Define project objectives, scope, and deliverables; align with SMART goals.
1.2 | Project Initiation | Scope Definition | Identify in-scope and out-of-scope activities based on West Yorkshire dataset.
1.3 | Project Initiation | Business Case | Develop justification for AI-based crime prediction model and expected benefits.
1.4 | Project Initiation | Risk Identification | List initial project risks (data quality, ethics, resource, scope creep).
1.5 | Project Initiation | Team Formation | Assign project roles (Scrum Master, developers, data analysts).
2.0 | Project Planning |  | Plan schedule, resources, and management activities.
2.1 | Project Planning | Work Breakdown Structure | Create WBS for the full project phases and milestones.
2.2 | Project Planning | Gantt Chart & Jira Setup | Define 8 sprints, tasks, dependencies, and deadlines.
2.3 | Project Planning | Budget & Resource Estimation | Estimate labour, cloud, and software costs.
2.4 | Project Planning | Risk Assessment & Mitigation | Develop risk matrix with likelihood, impact, and mitigation strategy.
2.5 | Project Planning | Communication Plan | Plan stakeholder meetings, updates, and reporting frequency.
3.0 | Data Preparation |  | Collect, clean, and prepare data for modeling.
3.1 | Data Preparation | Data Collection | Obtain dataset (2018–2024) from data.police.uk.
3.2 | Data Preparation | Data Cleaning | Handle missing values, inconsistencies, and normalize formats.
3.3 | Data Preparation | Exploratory Data Analysis | Analyze data distribution and detect patterns or correlations.
3.4 | Data Preparation | Data Visualization | Create heatmaps, trend graphs, and distribution plots.
4.0 | Model Development |  | Develop and test machine learning models.
4.1 | Model Development | Feature Engineering | Extract features (crime type, month, location).
4.2 | Model Development | Model Selection | Choose algorithms (Decision Tree, Random Forest, Logistic Regression).
4.3 | Model Development | Model Training & Testing | Train models, tune parameters, and evaluate test accuracy (target ≥ 80%).
4.4 | Model Development | Model Evaluation | Evaluate results with confusion matrix, recall, and precision metrics.
5.0 | Prototype Development |  | Build and test AI prototype.
5.1 | Prototype Development | Prototype Design | Develop front-end and back-end of AI prototype (Python/Colab).
5.2 | Prototype Development | Testing | Conduct unit, system, and user acceptance testing.
5.3 | Prototype Development | Documentation | Prepare technical documentation and GitHub README.
6.0 | Reporting & Delivery |  | Final reporting, demo, and reflection.
6.1 | Reporting & Delivery | Presentation Preparation | Create slides and visuals for final group presentation.
6.2 | Reporting & Delivery | Live Demo | Present prototype and explain methodology (April 6, 2026).
6.3 | Reporting & Delivery | Submission | Submit all files to Canvas (April 3, 2026).
6.4 | Reporting & Delivery | Individual Reflection | Write critical reflection report and literature review.
6.5 | Reporting & Delivery | FAIR Report | Document transparency of AI and GenAI tools used.