FUTURE AI FOR ALL (FALL)

PROJECT INITIATION DOCUMENT

Crime Hotspot Prediction System

West Yorkshire Police  |  COS-5031-E Discipline-Specific AI Project

University of Bradford  |  Dr Kulvinder Panesar

Version 2.0  |  March 2026  |  Group: Yr2DSP-B25

| PROJECT INITIATION DOCUMENT (PID) |  |
| --- | --- |
| Project Title | Crime Hotspot Prediction System |
| Client | West Yorkshire Police |
| Organisation | Future AI for ALL (FALL) — Internship Programme |
| Module | COS-5031-E Discipline-Specific AI Project (Level 5, 60 Credits) |
| Module Leader | Dr Kulvinder Panesar |
| Client Supervisor | Dr Irfan Mehmood |
| Project Manager | Alaedine Ait Bella |
| Team | Alaedine Ait Bella ¦ Reyad Taha ¦ Pana Sharif |
| Jira Board | CP (Crime Prediction) — 5 Sprints |
| GitHub | github.com/[team-repo] — open source, MIT licence |
| Methodology | Agile Scrum (5 sprints across 2 semesters) |
| Group Submission | Friday 17th April 2026 by 12pm (Canvas) |
| Presentation Date | Monday 20th April 2026 — D.1.03, all day, 20 min + 5 min Q&A |
| Document Version | v2.0 — Final (March 2026) |

# 1. Business Case and Problem Statement

Rubric: Assignment 1 rubric: Business case and stakeholders (2) ¦ Problem statement and scope (2) ¦ Domain knowledge and data availability (3)

## 1.1 Business Case

West Yorkshire is one of the largest metropolitan police force areas in England, covering Bradford, Leeds, Calderdale, Kirklees, and Wakefield. Reactive policing — deploying officers only after crimes are reported — is resource-intensive and insufficient to prevent crime in high-density urban areas. West Yorkshire Police require a data-driven decision-support tool that identifies the geographic areas most likely to experience elevated crime in the coming month, enabling proactive and targeted patrol allocation.

This project develops a machine learning-based Crime Hotspot Prediction System for West Yorkshire Police, using publicly available crime records from data.police.uk (Open Government Licence v3.0). The system forecasts which 500m grid cells across West Yorkshire are at the highest risk of crime one month ahead, ranked by predicted crime likelihood. It is designed as a decision-support tool — advisory, interpretable, and human-in-the-loop — not an automated enforcement system.

## 1.2 Stakeholders

| Stakeholder | Type | Interest | Engagement |
| --- | --- | --- | --- |
| West Yorkshire Police | Primary Client | Operational use of hotspot predictions to guide patrol allocation | Sprint reviews, client showcase 20 Apr 2026 |
| Dr Irfan Mehmood | Client Rep | Academic oversight; validates problem relevance and solution fit | Feedback sessions, progress reports |
| Dr Kulvinder Panesar | Module Leader | Academic assessment; quality of AI methods, PM approach, ethics | Supervisions, formative feedback |
| General Public | Indirect | Affected by patrol allocation decisions made using the system | N/A — protected by FAST ethical framework |
| data.police.uk | Data Provider | Open-licence source of West Yorkshire crime records | Open Government Licence v3.0 |

## 1.3 Problem Statement

Reactive policing is insufficient to prevent crime in resource-constrained environments. West Yorkshire Police need a reproducible, interpretable, and ethically sound AI system that ranks geographic cells by predicted crime risk one month ahead, supporting proactive patrol allocation decisions. The system must comply with UK GDPR Article 22 (no automated individual-level enforcement), ICO AI guidance (interpretability required), and the Alan Turing Institute FAST principles (Fairness, Accountability, Sustainability, Transparency).

## 1.4 Domain Knowledge and Data Availability

The dataset is sourced from data.police.uk and contains 1,048,575 crime records from West Yorkshire Police covering January 2018 to January 2024. It is available under the Open Government Licence v3.0. The table below describes the 12 dataset columns:

| Column | Data Type | Notes |
| --- | --- | --- |
| Crime ID | string | Sparse unique identifier — excluded from modelling (15% null) |
| Month | string | Format YYYY-MM — parsed to datetime64 during ingestion |
| Longitude / Latitude | float64 | WGS84 coordinates — snapped to 500m x 500m grid cells |
| LSOA code / name | string | Lower Super Output Area — used for regional context only, not modelling output |
| Crime type | string | 14 categories — Violence and sexual offences is most prevalent category |
| Last outcome category | string | Investigation status — ~15% missing; 'Unable to prosecute suspect' is most common outcome |
| Context | string | 97% null — dropped entirely from all pipeline stages |

Key domain knowledge informing the modelling approach includes: routine activity theory (Cohen and Felson, 1979) — crime is more likely where capable guardianship is absent; crime pattern theory (Brantingham and Brantingham, 1984) — criminals operate within awareness spaces that can be mapped spatially; and near-repeat victimisation — crime clusters spatially and temporally, justifying lag and rolling features.

# 2. Aims, Objectives, and Outcomes

Rubric: Assignment 1 rubric: Aims and objectives and outcomes (3) ¦ Research methodology for the entire project (2)

## 2.1 SMART Goal

| Element | Description |
| --- | --- |
| Specific | Build a machine learning pipeline using Ridge Regression and CNN-GRU to predict which 500m grid cells in West Yorkshire have the highest crime likelihood one month ahead, using data from data.police.uk (Jan 2018 to Jan 2024). |
| Measurable | Primary metric: Precision@K (target >0.70). Secondary: MAE, RMSE, RMSLE, NDCG@K, PAI, PEI — all measured via walk-forward validation across 12 monthly test folds. |
| Attainable | Achievable using open-source West Yorkshire crime data (Open Government Licence v3.0), standard Python ML libraries (scikit-learn, PyTorch), and university-grade computing infrastructure within a 9-month internship period. |
| Relevant | Directly addresses the client problem: reactive policing is resource-intensive. A data-driven hotspot ranking system enables proactive patrol allocation, reducing crime and improving public safety outcomes in West Yorkshire. |
| Time-Bound | All deliverables submitted by Friday 17th April 2026 (12pm, Canvas). Live demo and client presentation on Monday 20th April 2026 in D.1.03. |

## 2.2 Project Aims

- Explore existing crime prediction methods and responsible AI frameworks applicable to policing

- Source, clean, and engineer spatio-temporal features from the West Yorkshire crime dataset

- Build and rigorously evaluate baseline and advanced ML forecasting models using walk-forward validation

- Develop an interactive crime hotspot dashboard for operational decision-support use by West Yorkshire Police

- Ensure the solution meets ethical, legal, and responsible AI requirements throughout development

- Document all decisions for auditability, reproducibility, and academic assessment

## 2.3 Project Outcomes

- Trained Ridge Regression model — primary operational model (Precision@K = 0.731, NDCG@K = 0.958)

- Trained CNN-GRU deep learning benchmark model (MAE = 2.041)

- Walk-forward validation logs for all models stored in validation/wf_*.csv (12 monthly folds)

- Interactive Leaflet.js hotspot map deployed on Netlify with FastAPI backend on Render

- FAST ethical toolkit analysis documented in docs/ethical_toolkit.md

- Full open-source pipeline published on GitHub under MIT licence

## 2.4 Research Methodology

| Stage | Methodology |
| --- | --- |
| Literature Review | Systematic review of crime prediction methods: predictive policing literature, spatial criminology (routine activity theory, crime pattern theory), hotspot analysis, and responsible AI in law enforcement |
| Data Collection | Secondary data sourced from data.police.uk (open licence). West Yorkshire Police records, Jan 2018 to Jan 2024. 1,048,575 rows, 12 columns, CSV format |
| Exploratory Analysis | Descriptive statistics, geographic heatmaps, crime type distributions, monthly trend analysis, correlation analysis between crime type and outcome, location-based counts |
| Feature Engineering | Spatial grid aggregation (500m cells), temporal lag features (1-month, 12-month), rolling 3-month mean, spatial adjacency features. Temporal leakage prevention verified throughout |
| Model Development | Baseline models (Lag-1, Lag-12), Ridge Regression (primary), CNN-GRU (benchmark). Walk-forward expanding window validation across 12 monthly test folds (Jan to Dec 2024) |
| Evaluation | Regression metrics (MAE, RMSE, RMSLE, Poisson Deviance) and hotspot ranking metrics (Precision@K, Recall@K, NDCG@K, PAI, PEI) — all computed per fold and averaged |
| Ethical Analysis | Alan Turing Institute FAST Principles framework applied systematically. UK GDPR Art. 22, ICO AI guidance, ACM Code of Ethics, and UK AI Safety Act 2024 referenced |

# 3. Agile Project Management Framework

Rubric: Assignment 1 rubric: Agile PM overview (2) ¦ Project Plan – phase discussions (2) ¦ Sprint Plan reviews (4) ¦ Resources allocation and cost estimation (2) ¦ Risk assessment (2) ¦ Teamwork cohesiveness (2)

## 3.1 Agile Scrum Overview

The project follows an Agile Scrum methodology across 5 sprints spanning two semesters. Scrum was chosen because the project requirements evolved incrementally — early sprints focused on data engineering and EDA, later sprints on advanced modelling and deployment. Agile's iterative nature allowed continuous testing and model refinement between client feedback sessions.

Ceremonies: Sprint planning (start of each sprint), weekly standups (Monday, 15 minutes), sprint reviews with client feedback, and sprint retrospectives for team improvement. Tools: Jira for backlog management (CP board), GitHub for version control, Microsoft Teams for communication.

## 3.2 Sprint Plan

| Sprint | Period | Phase | Key Activities | Status |
| --- | --- | --- | --- | --- |
| 1 | Oct – Nov 2025 | Initiation | Project charter, PID creation, client interview, team contract, GitHub setup, Jira board configuration (CP epics), EDA planning, dataset sourcing from data.police.uk | Done |
| 2 | Nov – Dec 2025 | Data Engineering | Data ingestion (1,048,575 rows), cleaning, geographic bounding box validation, grid cell assignment (500m), PII removal, Context column dropped, EDA notebooks completed | Done |
| 3 | Jan 2026 | Feature Eng. + Baseline Models | Lag-1 and Lag-12 features, rolling 3-month mean, spatial adjacency features, no-leakage validation, Lag-1 and Lag-12 baseline models trained and walk-forward evaluated | Done |
| 4 | Feb – Mar 2026 | Advanced Models + Dashboard | Ridge Regression model trained and validated (Precision@K = 0.731), CNN-GRU deep learning benchmark, FastAPI backend deployed on Render, Leaflet.js dashboard deployed on Netlify | Done |
| 5 | Mar – Apr 2026 | QA, Ethics + Reporting | FAST ethical toolkit analysis, testing plan and master testing table, walk-forward validation final logs, PID completion, group blog finalisation, presentation and demo preparation | In Progress |

## 3.3 Jira Epics and Backlog

| Epic Key | Epic Name | Sprint | Status |
| --- | --- | --- | --- |
| CP-1 | Data Ingestion and Grid Creation | Sprint 2 | Done |
| CP-14 | Feature Engineering | Sprint 3 | Done |
| CP-27 | Baseline Modelling (Lag-1, Lag-12) | Sprint 3 | Done |
| CP-40 | Advanced Modelling (Ridge + CNN-GRU) | Sprint 4 | Done |
| CP-53 | Evaluation and Walk-Forward Validation | Sprint 4 | Done |
| CP-66 | API and Frontend Deployment | Sprint 4 | Done |
| CP-76 | Demo and Reporting | Sprint 5 | In Progress |
| CP-77 | Ethics Review, QA Testing, PID Completion | Sprint 5 | In Progress |

## 3.4 Key Milestones

| Milestone | Target Date | Status |
| --- | --- | --- |
| Project charter and PID created | Sprint 1 — Oct 2025 | Done |
| Dataset sourced, cleaned, EDA complete | Sprint 2 — Dec 2025 | Done |
| Baseline models trained and evaluated | Sprint 3 — Jan 2026 | Done |
| Ridge Regression and CNN-GRU complete | Sprint 4 — Mar 2026 | Done |
| Dashboard deployed (Render + Netlify) | Sprint 4 — Mar 2026 | Done |
| Ethics review and QA testing complete | Sprint 5 — Apr 2026 | In Progress |
| Group submission to Canvas | Friday 17th April 2026 by 12pm | Planned |
| Client presentation and live demo | Monday 20th April 2026, D.1.03 | Planned |

## 3.5 Team Roles and Responsibilities

| Name | Role | Responsibilities |
| --- | --- | --- |
| Alaedine Ait Bella | Project Manager / Lead ML Engineer | Project charter, PID, data pipeline, EDA, feature engineering, Ridge Regression and CNN-GRU modelling, walk-forward validation, GitHub, presentation lead |
| Reyad Taha | Data Engineer / Ethics Lead | Data cleaning, missing value handling, PII screening, FAST ethical audit, evaluation and ablation analysis, blog entries |
| Pana Sharif | Frontend / API Developer | FastAPI backend, Leaflet.js dashboard, Render deployment, Netlify hosting, CORS configuration, UI testing |

## 3.6 Resource Allocation and Cost Estimation

Cost estimation uses a Three-Point Estimation approach: Optimistic (O = £32,400), Most Likely (M = £40,500), Pessimistic (P = £60,750). Expected Cost = (O + 4M + P) / 6 = £44,550. Cloud services add £90 for Render hosting over 9 months.

| Resource | Category | Allocation | Unit Cost | Total (9 months) |
| --- | --- | --- | --- | --- |
| Alaedine Ait Bella | Labour (Direct) | 3 days/week (0.6 FTE) | £30,000/yr intern rate | £13,500 |
| Reyad Taha | Labour (Direct) | 3 days/week (0.6 FTE) | £30,000/yr intern rate | £13,500 |
| Pana Sharif | Labour (Direct) | 3 days/week (0.6 FTE) | £30,000/yr intern rate | £13,500 |
| Cloud Hosting (Render) | Infrastructure | Free tier + Pro | ~£10/month | £90 |
| Netlify (Frontend) | Infrastructure | Free tier | £0 | £0 |
| GitHub, Python, Jupyter | Software (Fixed) | Open source | £0 | £0 |
| TOTAL ESTIMATED BUDGET (Three-Point Average) |  |  |  | £44,640 |

## 3.7 Quality Plan

| Quality Dimension | Standard / Measure | Evidence |
| --- | --- | --- |
| Code Quality | All code version-controlled on GitHub. Clearly labelled: original / adapted / new | GitHub commit history, branch naming conventions |
| Model Quality | Walk-forward validation (no temporal leakage). Metrics: MAE, RMSE, Precision@K, NDCG@K, PAI, PEI | validation/wf_*.csv logs; notebooks/05_evaluation.ipynb |
| Data Quality | PII-free output confirmed. Grid assignment verified. Null columns removed. Bounding box validation applied | src/ingest.py; notebooks/01_eda.ipynb |
| Ethical Compliance | FAST principles (Fairness, Accountability, Sustainability, Transparency) applied. UK GDPR Art. 22 confirmed | docs/ethical_toolkit.md; group blog Sprint 5 entry |
| Documentation Quality | Harvard referencing throughout. 1.5 line spacing, font size 11, structured headings (3 levels max) | PID, individual reports, group blog, README.md |
| Presentation Quality | 20-minute presentation + 5-minute Q&A. Rehearsed delivery. Slide deck reviewed by full team | Slide deck submitted to Canvas by 17th April 2026 |

# 4. Risk Assessment and Management

Rubric: Assignment 1 rubric: Risk assessment discussion (2)

| # | Risk | Category | Likelihood / Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Data quality: Crime ID and Last Outcome Category columns have ~15% missing values; inconsistent location documentation | Data | High / High | Columns dropped or imputed where appropriate. Context column (97% null) removed entirely. PII-free grid aggregation used — individual record quality less critical at cell level |
| R2 | Ethical risk: model may amplify historical policing bias (e.g. over-policed areas appear as hotspots due to police presence, not higher underlying crime rates) | Ethical | High / High | System is advisory only — no automated enforcement. FAST principles applied throughout. Officers retain all decision-making authority. UK GDPR Art. 22 compliance confirmed |
| R3 | Scope creep: client may request additional features, analysis areas, or new crime categories beyond agreed prototype scope | PM | Medium / Medium | Scope clearly defined in PID. Change requests must be approved by Project Manager and logged in Jira. Sprint reviews used to manage client expectations |
| R4 | Resource risk: intern-led project — delays if team coordination breaks down or members are unavailable during critical sprint phases | PM | Medium / High | Team contract signed at Sprint 1. Weekly standups via Jira. Tasks allocated by skill set. Alaedine as PM manages cross-dependencies |
| R5 | Model performance risk: CNN-GRU may underperform on limited university-grade infrastructure; deep learning requires more compute than available | Technical | Medium / Medium | Ridge Regression designated as primary production model. CNN-GRU retained as benchmark only. Walk-forward validation detects underperformance early |
| R6 | Data leakage risk: temporal features incorrectly using future information could inflate model performance metrics | Technical | Low / High | Walk-forward (expanding window) validation enforced throughout. All feature time indices verified to be < forecast month. No random cross-validation used |

# 5. Constraints, Limitations, Opportunities, and Challenges

Rubric: Assignment 1 rubric: Constraints, limitations, opportunities, and challenges/issues (3)

| CONSTRAINTS |  |
| --- | --- |
| C1 | All project deadlines are fixed and non-negotiable (submission 17 Apr 2026, presentation 20 Apr 2026) |
| C2 | System must be explainable under ICO AI and Data Protection Guidance — black-box only models not acceptable for operational deployment |
| C3 | No automated individual-level enforcement — UK GDPR Article 22 compliance required throughout |
| C4 | Dataset limited to recorded West Yorkshire crime data (Jan 2018 to Jan 2024). No new primary data collection |
| C5 | Must run on standard university-grade infrastructure (no HPC or paid GPU compute beyond free tiers) |
| LIMITATIONS |  |
| L1 | Dataset reflects recorded crime only. Unreported crime cannot be modelled — areas with more police presence will appear as higher-crime areas regardless of underlying rate |
| L2 | Context column (97% null) excluded entirely. Last Outcome Category has ~15% missing values — limits outcome-based feature engineering |
| L3 | No ONS socio-economic features included in v1.0. Deprivation indicators planned as a future enhancement |
| L4 | CNN-GRU model not suitable for operational deployment under current ICO guidance due to reduced interpretability |
| OPPORTUNITIES |  |
| O1 | Open Government Licence dataset enables full reproducibility and reuse across other UK police force areas |
| O2 | Ridge Regression interpretability creates a clear pathway to operational deployment — coefficients can be audited by West Yorkshire Police analysts |
| O3 | System architecture is modular — ONS deprivation data, weather data, and event calendars could be integrated as additional features in a v2.0 |
| O4 | CNN-GRU benchmark establishes a strong foundation for future deep learning work if compute and interpretability requirements are met |

# 6. Project Scope

Rubric: Assignment 1 rubric: Problem statement and scope (2)

## 6.1 In Scope

- West Yorkshire crime data processing pipeline (Jan 2018 to Jan 2024, 1,048,575 records)

- 500m x 500m spatial grid generation covering Bradford, Leeds, Calderdale, Kirklees, Wakefield

- Feature engineering: lag features (1-month, 12-month), rolling 3-month mean, spatial adjacency

- Baseline model training and walk-forward validation (Lag-1, Lag-12)

- Ridge Regression model training and walk-forward validation (primary operational model)

- CNN-GRU deep learning model training and evaluation (benchmark only)

- FastAPI prediction backend deployed on Render

- Leaflet.js interactive dashboard deployed on Netlify

- FAST ethical toolkit analysis

- Full testing plan (30 test cases across 10 phases)

## 6.2 Out of Scope

- Individual-level crime prediction or identification of potential offenders

- Real-time or live-streaming crime monitoring (system forecasts one month ahead only)

- Automated policing decisions — system is advisory only, human officer in the loop required

- Analysis of crime data outside West Yorkshire or beyond January 2024

- Production-grade infrastructure (system is a prototype for academic and client demonstration)

- Collection of new primary data or integration of commercial data sources

# 7. Key Deliverables

Rubric: Assignment 1 rubric: Demo plan (6) ¦ Testing evidence (4) ¦ Validation evidence (4)

| Deliverable | Description | Status |
| --- | --- | --- |
| Data pipeline (src/ingest.py, src/features.py) | Cleans, grids, and engineers features from raw CSV data | Done |
| Baseline models (wf_baseline_lag1.csv / lag12.csv) | Walk-forward validated Lag-1 and Lag-12 baselines | Done |
| Ridge Regression model (src/models/ridge.py) | Primary operational model — interpretable, auditable | Done |
| CNN-GRU model (src/models/cnn_gru.py) | Deep learning benchmark — higher accuracy, lower interpretability | Done |
| Walk-forward validation logs (validation/wf_*.csv) | 12 monthly folds logged for full audit trail | Done |
| FastAPI backend (crime_map_app/backend/app.py) | Serves /predict, /predict_point, /months endpoints | Done |
| Leaflet.js dashboard (crime-map/) | Interactive hotspot map with adjustable threshold | Done |
| FAST Ethical Toolkit (docs/ethical_toolkit.md) | Fairness, Accountability, Sustainability, Transparency analysis | Done |
| Testing Plan and Master Testing Table | 30 test cases across 10 phases, all pass criteria documented | Done |
| Project Initiation Document (PID) | This document — all sections complete | In Progress |
| Group presentation and live demo | 20 min + 5 min Q&A on 20th April 2026 | Planned |

# 8. Team Contract and Cohesiveness

Rubric: Assignment 1 rubric: Teamwork cohesiveness and Group work activities (2) ¦ Team contract

| Agreement | Detail |
| --- | --- |
| Communication | Weekly standup via Microsoft Teams every Monday. Jira used for task tracking. WhatsApp group for urgent communication |
| Task Allocation | Tasks assigned at sprint planning based on role and workload. All assignments logged in Jira backlog with story points |
| Code Standards | All code committed to GitHub with clear labels (original / adapted / new). Pull requests reviewed before merging to main |
| Deadlines | Internal deadlines set 3 days before official submission dates to allow review. Late delivery must be flagged to PM at least 48 hours in advance |
| Conflict Resolution | Disagreements resolved by majority vote in team meeting. If unresolved, escalated to module supervisor Dr Kulvinder Panesar |
| Blog Entries | Group blog updated at end of each sprint. Individual blogs updated fortnightly minimum as per assignment brief requirements |

## 8.1 Group Work Activities

- Sprint 1: Joint client interview preparation. Team contract signed. Roles and responsibilities agreed. GitHub repository shared with module team

- Sprint 2: Pair review of EDA notebooks. Data quality issues (null columns, location inconsistencies) discussed and mitigation decisions agreed jointly

- Sprint 3: Feature engineering approach peer-reviewed. Temporal leakage prevention strategy agreed by full team before model training commenced

- Sprint 4: Model selection decision made jointly — Ridge Regression chosen as primary model based on interpretability under ICO guidance. CNN-GRU retained as benchmark

- Sprint 5: FAST ethical toolkit written collaboratively. Testing plan reviewed by full team. Presentation structure agreed and rehearsal scheduled

# 9. Success Criteria and OKRs

| Objective | Key Results (Measurable) |
| --- | --- |
| Build a reliable, leakage-free crime forecasting pipeline | 1. Raw CSVs processed to parquet with zero PII fields 2. Grid cell assignment verified (zero null cell_id) 3. Walk-forward validation confirms zero temporal leakage 4. All 12 monthly validation folds logged in wf_*.csv |
| Develop accurate, interpretable forecasting models | 1. Ridge Regression: Precision@K = 0.731, NDCG@K = 0.958, PEI = 0.946 2. CNN-GRU benchmark: MAE = 2.041 (lower than Ridge) 3. Both models outperform Lag-1 and Lag-12 baselines on ranking metrics 4. Ridge selected as primary model per ICO interpretability guidance |
| Deliver an operational decision-support tool | 1. FastAPI backend deployed on Render — /predict, /predict_point, /months endpoints live 2. Leaflet.js dashboard deployed on Netlify — hotspot overlay renders within 3 seconds 3. System advisory-only confirmed — no automated enforcement output at any endpoint |
| Ensure responsible and ethical AI | 1. FAST principles analysis completed and documented 2. UK GDPR Article 22 compliance confirmed 3. No PII in any pipeline output verified by code review 4. Walk-forward audit trail retained in validation/ directory |

# 10. Document Approvals

The undersigned parties confirm they have reviewed this Project Initiation Document and authorise the project to proceed on the terms described above.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Client | Dr Irfan Mehmood |  |  |
| Module Leader | Dr Kulvinder Panesar |  |  |
| Project Manager | Alaedine Ait Bella |  |  |
| Team Member | Reyad Taha |  |  |
| Team Member | Pana Sharif |  |  |